VANGUARD STRATEGISTS

PROJECT MANAGEMENT DOCUMENTATION PACKAGE

Biodiversity & Native Planting Planner

# 1. Project Plan

## 1.1 Project Overview

The Biodiversity & Native Planting Planner supports UN SDG Goal 15: Life on Land by helping urban gardeners identify and select native plant species that support local pollinators and biodiversity. The project provides automated recommendations and visual planning tools for sustainable garden design.

## 1.2 Project Goals

- Increase awareness and adoption of native plant species by 20% by EOY.

- Support pollinator populations through biodiversity-friendly planting decisions.

- Provide a user-friendly visual planning tool.

- Deliver accurate, data-driven plant recommendations.

- Promote sustainable urban gardening practices.

## 1.3 Scope

| In Scope | Out of Scope |
| --- | --- |
| Research and integration of native plant and pollinator datasets | Plant sales |
| Recommendation algorithms | Landscaping services |
| Visual planning features | Maintenance scheduling |
| Security assessments | Mobile app development beyond project scope |
| User research and market analysis |  |

## 1.4 Team Structure, Responsibilities & Deliverables

| Team Member | Role | Core Responsibilities | Assigned Deliverables |
| --- | --- | --- | --- |
| Jennifer Okpalaeze | Project Manager | Project planning; timeline; stakeholder communication; risk management; sprint planning; coordination | Project charter; Project Plan documentation; schedule; meeting summary; risk register; progress reports |
| Rofiat Onifade | Data Analyst | Research and prepare native plant and pollinator datasets; define data quality standards; analyze user research; support recommendation logic | Cleaned datasets; data dictionary; analytics dashboard; recommendation criteria |
| Adesuyi Emmanuel Omole | Cybersecurity Analyst | Identify security/privacy risks; recommend secure authentication if accounts are included; assess data protection needs; ensure privacy best practices | Risk assessment; security requirements; threat model; security testing checklist |
| Notewo Nze Nelson Thierry | IT Automation with Python | Build data processing scripts; automate data collection/cleaning where permitted; develop recommendation algorithms/backend automation; integrate APIs | Python scripts; automated workflows; backend logic; API integrations |
| Emmanuel Anowi | Marketing & E-commerce | Market research; target users; branding; communication plan; outreach strategy; user adoption plan | User personas; competitor analysis; marketing strategy; promotional materials; presentation support |

## 1.5 Deliverable Ownership Matrix

| Deliverable | Primary Team Owner(s) | Supporting Team Member(s) |
| --- | --- | --- |
| Interactive planning application | Notewo Nze Nelson Thierry | Rofiat Onifade; Emmanuel Anowi; Adesuyi Emmanuel Omole; Jennifer Okpalaeze |
| Native plant and pollinator database | Rofiat Onifade | Notewo Nze Nelson Thierry; Jennifer Okpalaeze |
| Recommendation engine | Notewo Nze Nelson Thierry | Rofiat Onifade; Adesuyi Emmanuel Omole |
| Automated workflows and API integrations | Notewo Nze Nelson Thierry | Rofiat Onifade; Adesuyi Emmanuel Omole |
| Security and privacy documentation | Adesuyi Emmanuel Omole | Jennifer Okpalaeze; Notewo Nze Nelson Thierry |
| Marketing and user adoption strategy | Emmanuel Anowi | Jennifer Okpalaeze; Rofiat Onifade |
| Final project documentation and presentation | Jennifer Okpalaeze | All team members |

## 1.6 Project Governance & Change Control

- PM coordinates planning, timelines, stakeholder communication, sprint planning, risks, meetings, and overall project coordination.

- Each team member reports progress, dependencies, risks/issues, and required decisions to the Project Manager.

- Changes affecting scope, schedule, quality, security/privacy, or deliverables are documented and reviewed before being incorporated into the plan.

- Requests involving excluded activities, plant sales, landscaping services, maintenance scheduling, or out-of-scope mobile development remain outside the baseline unless formally approved through change control.

- Security/privacy concerns identified by Adesuyi Emmanuel Omole are tracked through the project risk and issue process.

# 2. Project Schedule

The project charter does not provide detailed start/finish dates. The following is a proposed phase-based schedule for team validation. PM owns schedule coordination and updates.

| Phase | Indicative Timing | Lead | Key Activities | Milestone |
| --- | --- | --- | --- | --- |
| 1. Initiation & planning | Weeks 1-2 | Jennifer Okpalaeze | Confirm scope, stakeholders, work plan, sprint approach, risks and reporting | Project baseline approved |
| 2. Data research & preparation | Weeks 2-3 | Rofiat Onifade | Research datasets, data quality standards, cleaning, data dictionary, analytics | Dataset baseline ready |
| 3. Automation & backend development | Weeks 3–4 | Notewo Nze Nelson Thierry | Python scripts, data processing, recommendation/backend logic, API integration | Backend/integration build complete |
| 4. Security & privacy planning | Weeks 4–5 | Adesuyi Emmanuel Omole | Risk assessment, security requirements, threat model, privacy considerations | Security requirements approved |
| 5. Product/user research & adoption | Weeks 6-7 | Emmanuel Anowi | Personas, competitor analysis, user research analysis, branding, outreach and adoption plan | Adoption strategy ready |
| 7. Finalization & presentation | Weeks 7-8 | Jennifer Okpalaeze + Emmanuel Anowi | Final documentation, performance results, presentation and closure | Project closed |

## 2.1 Schedule Control

- PM maintains the master schedule and tracks planned versus actual dates.

- Each workstream reports completion, next activities, dependencies and blockers during status meetings.

- Critical-path slippage is escalated promptly to the team for corrective action.

- Approved changes are reflected in the schedule baseline and change log.

# 3. Meeting Summary & Action Log

| Meeting | Lead | Participants | Purpose / Agenda | Output |
| --- | --- | --- | --- | --- |
| Project kickoff | Jennifer Okpalaeze | All team members | Objectives, scope, deliverables, responsibilities, schedule, risks | Baseline and action list |
| Weekly project status | Jennifer Okpalaeze | All team members | Progress, schedule, risks, dependencies, decisions, next sprint | Status report + action log |
| Data & recommendation review | Rofiat Onifade | All team members | Data quality, data dictionary, recommendation criteria | Data/recommendation decisions |
| Integration | Notewo Nze Nelson Thierry | All team members | Automation, APIs, backend, test readiness, security checks | Python scripts, automated workflows, backend logic, API integrations |
| Security review | Adesuyi Emmanuel Omole | All team members | Threats, privacy, security requirements, testing checklist | Security actions/decision |
| Marketing & adoption review | Emmanuel Anowi | All team members | Personas, market research, branding, outreach, adoption | Marketing/adoption decisions |
| Project closure | Jennifer Okpalaeze | All team members | Deliverables, performance, lessons learned, handover, closure | Closure approval |

# 4. Risk Register

| ID | Risk | Owner | P | I | Mitigation / Response |
| --- | --- | --- | --- | --- | --- |
| R-01 | Native plant/pollinator datasets may be incomplete, inconsistent or difficult to integrate. | Rofiat Onifade | M | H | Define data quality standards early; document sources; clean and validate datasets. |
| R-02 | Recommendation logic may produce inaccurate recommendations. | Rofiat Onifade / Notewo Nze Nelson Thierry | M | H | Define recommendation criteria; validate data and logic against agreed test cases. |
| R-03 | Automation/API integrations may fail or be delayed. | Notewo Nze Nelson Thierry | M | M | Prototype high-risk integrations early; use integration testing and documented fallback handling. |
| R-04 | Security or privacy weaknesses may be identified late. | Adesuyi Emmanuel Omole | M | H | Complete risk assessment, security requirements and threat model early; track remediation. |
| R-05 | User needs may not be sufficiently reflected in the planning tool. | Rofiat Onifade / Emmanuel Anowi | M | M | Analyze user research; define personas and use findings in planning and adoption decisions. |
| R-06 | Marketing and adoption activities may not achieve the 20% target. | Emmanuel Anowi | M | H | Establish adoption baseline and KPIs; align outreach and promotional activities to measurable outcomes. |
| R-07 | Scope expands into excluded services or mobile development. | Jennifer Okpalaeze | M | M | Apply change control and maintain explicit scope boundaries. |
| R-08 | Team capacity or dependencies cause schedule slippage. | Jennifer Okpalaeze | M | M | Track sprint commitments, dependencies and blockers; re-prioritize and escalate as needed. |
| R-09 | Security testing or technical validation identifies release-blocking issues. | Adesuyi Emmanuel Omole / Notewo Nze Nelson Thierry | M | H | Use security testing checklist, severity-based remediation and release readiness review. |
| R-10 | Final project documentation or presentation is incomplete. | Jennifer Okpalaeze | L | M | Maintain documentation throughout delivery and use a closure checklist. |

# 5. Project Closing

| Closure Item | Responsible Team Member | Evidence | Status |
| --- | --- | --- | --- |
| Project documentation and final plan | Jennifer Okpalaeze | Approved final documentation | Complete |
| Schedule and project records | Jennifer Okpalaeze | Final schedule and project records | Complete |
| Cleaned datasets/data dictionary/analytics | Rofiat Onifade | Data package and supporting analysis | Complete |
| Recommendation criteria | Rofiat Onifade | Criteria and validation evidence | Complete |
| Security risk assessment | Adesuyi Emmanuel Omole | Risk assessment | Complete |
| Security requirements/threat model | Adesuyi Emmanuel Omole | Security documentation | Complete |
| Security testing checklist | Adesuyi Emmanuel Omole | Completed checklist | Complete |
| Python scripts/automated workflows | Notewo Nze Nelson Thierry | Code/scripts and workflow evidence | Complete |
| Backend logic/API integrations | Notewo Nze Nelson Thierry | Integration evidence | Complete |
| User personas/competitor analysis | Emmanuel Anowi | Research package | Complete |
| Marketing/adoption strategy | Emmanuel Anowi | Approved strategy | Complete |
| Promotional materials/presentation support | Emmanuel Anowi | Final materials | Complete |
| Final presentation and closure | Jennifer Okpalaeze + Emmanuel Anowi | Final presentation | Complete |
| Lessons learned | Jennifer Okpalaeze | Lessons-learned record | Complete |
| Formal closure approval | Jennifer Okpalaeze | Sign-off | Complete |

## 5.1 Charter Deliverable Closure

| Charter Deliverable | Closure Evidence | Status |
| --- | --- | --- |
| Interactive planning application | Application/release evidence and acceptance | Complete |
| Native plant and pollinator database | Cleaned datasets, data dictionary | Complete |
| Recommendation engine | Recommendation criteria + backend logic + validation | Complete |
| Automated workflows and API integrations | Python scripts, workflows, API evidence | Complete |
| Security and privacy documentation | Risk assessment, requirements, threat model, checklist | Complete |
| Marketing and user adoption strategy | Personas, competitor analysis, strategy, promotional materials | Complete |
| Final project documentation and presentation | Final project package and presentation | Complete |

## 5.2 Closing Statement

Project closure date: August 21, 2026. The Biodiversity & Native Planting Planner is declared Complete following review of the charter deliverables, team-owned work products, performance results, risks/issues, documentation, lessons learned and required handover..

# 6. Lessons Learned

| Area | What worked | Challenge | Lesson / Recommendation | Owner |
| --- | --- | --- | --- | --- |
| Project management | Clear assignment of planning, scheduling, stakeholder communication, risk management, sprint planning, and coordination helped maintain project structure and accountability. | Managing dependencies across data, security, automation, and marketing activities could affect timelines when one workstream experienced delays. | Identify and track cross-functional dependencies early. Review the project schedule, risks, blockers, and priorities regularly during sprint planning and status meetings. | Jennifer Okpalaeze |
| Data | Clear ownership of native plant and pollinator research, data preparation, data quality standards, user research analysis, and recommendation criteria supported data-driven decision-making. | Data from different sources may require cleaning, standardization, validation, and documentation before being used reliably in recommendations. | Establish data quality standards, validation rules, source documentation, and a data dictionary early in the project. Validate data before using it in recommendation logic. | Rofiat Onifade |
| Security/privacy | Security and privacy responsibilities were assigned to a dedicated team member, supporting early identification of risks and protection requirements. | Security and privacy requirements may evolve as backend automation, APIs, authentication, and data-processing requirements become clearer. | Incorporate security and privacy requirements into planning and technical design from the beginning. Complete risk assessments, threat modelling, and security testing before release. | Adesuyi Emmanuel Omole |
| Automation/backend | Python automation, backend logic, recommendation algorithms, and API integrations created a foundation for efficient data processing and automated functionality. | Automation and recommendation logic depend on reliable data and may be affected by API limitations, integration issues, or changing technical requirements. | Validate recommendation criteria and data before automation. Test integrations early and use representative test cases to confirm that automated workflows operate as intended. | Notewo Nze Nelson Thierry |
| Marketing/adoption | Market research, user personas, competitor analysis, branding, communication, outreach, and adoption planning helped connect the project solution with its intended users. | Developing a useful solution does not automatically guarantee achievement of the project's 20% awareness and adoption target. | Define the adoption baseline and performance measures early. Use user research and market feedback to continuously improve outreach and adoption activities. | Emmanuel Anowi |
| Team coordination | The five-person team had clearly defined responsibilities and deliverables, supporting accountability and cross-functional collaboration. | Different technical and business areas required regular communication to ensure that data, security, automation, project management, and marketing activities remained aligned. | Maintain regular status meetings and concise meeting summaries that record decisions, actions, owners, due dates, risks, and dependencies. | Jennifer Okpalaeze |

# 7. Approval & Sign-off

| Team Member | Role | Signature | Date |
| --- | --- | --- | --- |
| Jennifer Okpalaeze | Project Manager | _____jennOkpaleze______ | ___21–08-26_____ |
| Rofiat Onifade | Data Analyst | ________________ | ________ |
| Adesuyi Emmanuel Omole | Cybersecurity Analyst | ________________ | ________ |
| Notewo Nze Nelson Thierry | IT Automation with Python | ________________ | ________ |
| Emmanuel Anowi | Marketing & E-commerce | ________________ | ________ |