## WBS
BRAID (EQUITABLE MENTORSHIP PAIRING ENGINE) WORK BREAKDOWN SYSTEM
WBS ID | Phase | Activity / Task | Team Member(s) Responsible | Duration | Expected Output
1 | PHASE 1: PROJECT INITIATION & DISCOVERY | Establish the foundation for Project; Braid (EMPE) | Benardette + Entire Team | 7 days | Clear project direction, scope and requirements
1.1 |  | Confirm problem statement, vision and objectives | Benardette | 1 day | Agreed project direction
1.2 |  | Validate the mentorship accessibility problem | Benardette + Eulleria | 2 days | Validated problem
1.3 |  | Identify and define project's target users | Benardette + Eulleria | 2 days | Mentor and mentee user profiles
1.4 |  | Identify mentor and mentee needs | Benardette + Eulleria | 2 days | User requirements
1.5 |  | Identify information required for effective matching | Eulleria | 1 day | Matching data requirements
1.6 |  | Define Project's MVP and priority features | Benardette + Entire Team | 2 days | Approved MVP scope
1.7 |  | Identify initial security and privacy considerations | Jeff | 1 day | Initial security requirements
1.8 |  | Confirm technical feasibility and development approach | Omogbolaga + Jeff | 1 day | Technical direction
1.9 |  | Assign responsibilities and establish team workflow | Benardette | 1 day | Team responsibility structure
1.1 |  | Establish project milestones and working schedule | Benardette | 1 day | Project roadmap
2 | PHASE 2: PRODUCT & SYSTEM DESIGN | Translate the project concept into a buildable solution | Entire Team | 7 days | Product, data, matching and system design
2.1 |  | Design mentor profile structure | Eulleria + Omogbolaga | 1 day | Mentor profile fields
2.2 |  | Design mentee profile structure | Eulleria + Omogbolaga | 1 day | Mentee profile fields
2.3 |  | Define participant data fields and data structure | Eulleria | 2 days | Participant data model
2.4 |  | Map mentor and mentee user journeys | Benardette + Eulleria | 1 day | User journey
2.5 |  | Design onboarding and profile workflow | Benardette + Omogbolaga | 1 day | Onboarding flow
2.6 |  | Design match discovery experience | Benardette + Omogbolaga | 1 day | Match discovery flow
2.7 |  | Identify compatibility factors | Eulleria | 1 day | Compatibility framework
2.8 |  | Define matching criteria and factor weights | Eulleria + Benardette | 2 days | Matching model
2.9 |  | Define mentor capacity considerations | Eulleria + Benardette | 1 day | Capacity rules
2.1 |  | Define equity considerations for matching | Benardette + Eulleria | 1 day | Equity criteria
2.11 |  | Define matching algorithm logic | Eulleria + Omogbolaga | 2 days | Matching logic specification
2.12 |  | Design system architecture | Omogbolaga + Jeff | 2 days | System architecture
2.13 |  | Define privacy, security and access requirements | Jeff | 1 day | Security requirements
2.14 |  | Review overall design against project's objectives | Entire Team | 1 day | Approved solution design
3 | PHASE 3: PLATFORM DEVELOPMENT | Build the Braids working MVP | Omogbolaga + Entire Team | 7 days | Functional Braids platform
3.1 |  | Set up development environment | Omogbolaga | 1 day | Development environment
3.2 |  | Build mentor profile functionality | Omogbolaga | 2 days | Functional mentor profile
3.3 |  | Build mentee profile functionality | Omogbolaga | 2 days | Functional mentee profile
3.4 |  | Implement participant data structure | Omogbolaga + Eulleria | 2 days | Functional data layer
3.5 |  | Prepare sample mentor and mentee datasets | Eulleria | 2 days | Test dataset
3.6 |  | Implement compatibility scoring model | Eulleria + Omogbolaga | 2 days | Compatibility scoring
3.7 |  | Implement matching algorithm | Omogbolaga + Eulleria | 3 days | Functional matching engine
3.8 |  | Integrate participant data with matching engine | Omogbolaga | 1 day | Integrated matching process
3.9 |  | Build match recommendation/discovery interface | Omogbolaga | 2 days | Match recommendations
3.1 |  | Build basic user dashboard | Omogbolaga | 2 days | Functional dashboard
3.11 |  | Apply security and privacy considerations | Jeff + Omogbolaga | 1 day | Protected MVP
3.12 |  | Integrate all core platform components | Omogbolaga + Entire Team | 2 days | Working Braids MVP
3.13 |  | Review MVP against approved requirements | Benardette + Entire Team | 1 day | MVP review
4 | PHASE 4: TESTING & OPTIMIZATION | Test, evaluate and improve Braids | Entire Team | 6 days | Validated and refined MVP
4.1 |  | Prepare realistic mentor and mentee test scenarios | Eulleria + Benardette | 1 day | Test scenarios
4.2 |  | Test mentor profile functionality | Omogbolaga | 1 day | Profile test results
4.3 |  | Test mentee profile functionality | Omogbolaga | 1 day | Profile test results
4.4 |  | Test participant data processing | Eulleria + Omogbolaga | 1 day | Data test results
4.5 |  | Test matching algorithm with different participant combinations | Eulleria + Omogbolaga | 2 days | Matching results
4.6 |  | Evaluate relevance of recommended matches | Eulleria + Benardette | 1 day | Match evaluation
4.7 |  | Review equity and fairness of recommendations | Benardette + Eulleria | 1 day | Fairness review
4.8 |  | Conduct security review | Jeff | 1 day | Security findings
4.9 |  | Conduct usability testing | Entire Team | 1 day | Usability findings
4.1 |  | Document technical and user issues | Benardette + Omogbolaga | 1 day | Issue log
4.11 |  | Refine matching logic based on findings | Eulleria + Omogbolaga | 2 days | Improved matching engine
4.12 |  | Fix identified platform issues | Omogbolaga | 2 days | Improved platform
4.13 |  | Conduct final end-to-end testing | Entire Team | 1 day | Final test results
5 | PHASE 5: DEMONSTRATION & DELIVERY | Prepare and deliver the final Braid project | Entire Team | 4 days | Final project and BUILD submission
5.1 |  | Conduct final platform review | Entire Team | 1 day | Final QA
5.2 |  | Finalize working project's prototype | Omogbolaga | 1 day | Demo-ready platform
5.3 |  | Finalize matching model and supporting data evidence | Eulleria | 1 day | Final matching evidence
5.4 |  | Finalize security and privacy documentation | Jeff | 1 day | Security documentation
5.5 |  | Complete project management documentation | Benardette | 2 days | Final PM documentation
5.6 |  | Prepare project presentation | Benardette + Entire Team | 2 days | Final presentation
5.7 |  | Prepare project (Braid) platform demonstration | Omogbolaga + Entire Team | 2 days | Demo flow
5.8 |  | Document project outcomes and impact | Benardette + Eulleria | 1 day | Project outcomes
5.9 |  | Review MMC BUILD submission requirements | Benardette | 1 day | Submission checklist
5.1 |  | Complete final project review | Entire Team | 1 day | Approved final submission
5.11 |  | Submit Braids project | Benardette + Entire Team | 1 day | Final Project submission

## Risk Register Management Plan
BRAID (EQUITABLE MENTORSHIP PAIRING ENGINE) RISK REGISTER
Risk ID | Risk | Likelihood | Impact | Risk Level | Mitigation / Response | Owner | Status
R01 | Poor quality or incomplete mentor/mentee profile data may result in unsuitable matches | Medium | High | High | Define clear profile requirements and validate required information before matching | Eulleria | Open
R02 | Matching algorithm may produce inaccurate or unsuitable recommendations | Medium | High | High | Test the matching logic with sample profiles and refine criteria based on results | Eulleria / Omogbolaga | Open
R03 | Insufficient number of mentors compared with mentees may leave some mentees unmatched | Medium | High | High | Monitor mentor/mentee ratios and provide an unmatched-user handling process | Benardette | Open
R04 | User privacy or personal data may not be adequately protected | Medium | High | High | Apply access controls, minimize unnecessary data collection and follow basic data-protection practices | Jeff | Open
R05 | Unauthorized access to user or administrative information | Low | High | Medium | Use authentication, role-based access and secure handling of credentials | Jeff | Open
R06 | Technical difficulties may delay implementation | Medium | High | High | Prioritize core functionality, identify technical dependencies early and maintain a simplified fallback approach | Omogbolaga | Open
R07 | Team members may have competing schedules or delayed contributions | Medium | Medium | Medium | Set clear responsibilities, deadlines and regular check-ins | Benardette | Open
R08 | Changes to project requirements may affect the planned solution | Medium | Medium | Medium | Document agreed requirements and assess changes before incorporating them | Benardette | Open
R09 | Limited testing time may prevent adequate validation of the matching process | Medium | High | High | Prepare test data early and prioritize matching and core user workflows | Eulleria / Omogbolaga | Open
R10 | Users may not understand or trust the recommended matches | Medium | Medium | Medium | Clearly explain match recommendations and allow users/admins to review or reject unsuitable matches | Benardette / Team | Open
R11 | Integration between technical components may not work as expected | Medium | Medium | Medium | Test components together before final review and resolve integration issues early | Omogbolaga / Jeff | Open
R12 | Project documentation may become inconsistent across team members | Medium | Medium | Medium | Use the agreed architecture and requirements as the reference for all project documents | Benardette | Open

## Gnatt Chart
⬜ Not Started ¦ 🟨 Ongoing ¦ 🟩 Completed¦ 🟩 Day Started
Task ID | Task | Owner | 15–18 Jul | 19–23 Jul | 24–29 Jul | 30Jul–4 Aug | 5–11 Aug | 12–14 Aug
| PHASE 1: Project Initiation & Discovery | Benardette + Team
1.1 | Confirm project's problem, vision & objectives | Benardette
1.2 | Validate mentorship accessibility problem | Benardette + Eulleria
1.3 | Define project's target users | Benardette + Eulleria
1.4 | Identify mentor & mentee needs | Benardette + Eulleria
1.5 | Identify information required for matching | Eulleria
1.6 | Define project's MVP & priority features | Benardette + Team
1.7 | Identify security & privacy considerations | Jeff
1.8 | Confirm technical feasibility | Omogbolaga + Jeff
1.9 | Assign responsibilities & workflow | Benardette
1.1 | Establish milestones & schedule | Benardette
2 | PHASE 2: Product & System Design | Entire Team
2.1 | Design mentor profile | Eulleria + Omogbolaga
2.2 | Design mentee profile | Eulleria + Omogbolaga
2.3 | Define participant data structure | Eulleria
2.4 | Map mentor & mentee journeys | Benardette + Eulleria
2.5 | Design onboarding & profile workflow | Benardette + Omogbolaga
2.6 | Design match discovery experience | Benardette + Omogbolaga
2.7 | Identify compatibility factors | Eulleria
2.8 | Define matching criteria & weights | Eulleria + Benardette
2.9 | Define mentor capacity considerations | Eulleria + Benardette
2.1 | Define equity considerations | Benardette + Eulleria
2.11 | Define matching algorithm logic | Eulleria + Omogbolaga
2.12 | Design system architecture | Omogbolaga + Jeff
2.13 | Define privacy/security requirements | Jeff
2.14 | Review & approve solution design | Entire Team
3 | PHASE 3: Platform Development | Omogbolaga + Team
3.1 | Set up development environment | Omogbolaga
3.2 | Build mentor profile | Omogbolaga
3.3 | Build mentee profile | Omogbolaga
3.4 | Implement participant data structure | Omogbolaga + Eulleria
3.5 | Prepare sample datasets | Eulleria
3.6 | Implement compatibility scoring | Eulleria + Omogbolaga
3.7 | Implement matching algorithm | Omogbolaga + Eulleria
3.8 | Integrate data with matching engine | Omogbolaga
3.9 | Build match recommendation interface | Omogbolaga
3.1 | Build basic user dashboard | Omogbolaga
3.11 | Apply security/privacy controls | Jeff + Omogbolaga
3.12 | Integrate core platform components | Omogbolaga + Team
3.13 | Review MVP against requirements | Benardette + Team
4 | PHASE 4: Testing & Optimization | Entire Team
4.1 | Prepare test scenarios | Eulleria + Benardette
4.2 | Test mentor profile | Omogbolaga
4.3 | Test mentee profile | Omogbolaga
4.4 | Test participant data processing | Eulleria + Omogbolaga
4.5 | Test matching algorithm | Eulleria + Omogbolaga
4.6 | Evaluate match relevance | Eulleria + Benardette
4.7 | Review matching equity/fairness | Benardette + Eulleria
4.8 | Conduct security review | Jeff
4.9 | Conduct usability testing | Entire Team
4.1 | Document issues | Benardette + Omogbolaga
4.11 | Refine matching logic | Eulleria + Omogbolaga
4.12 | Fix platform issues | Omogbolaga
4.13 | Final end-to-end testing | Entire Team
5 | PHASE 5: Demonstration & Delivery | Entire Team
5.1 | Conduct final platform review | Entire Team
5.2 | Finalize Braid prototype | Omogbolaga
5.3 | Finalize matching/data evidence | Eulleria
5.4 | Finalize security documentation | Jeff
5.5 | Complete PM documentation | Benardette
5.6 | Prepare project presentation | Benardette + Team
5.7 | Prepare platform demonstration | Omogbolaga + Team
5.8 | Document project outcomes | Benardette + Eulleria
5.9 | Review BUILD submission requirements | Benardette
5.1 | Complete final project review | Entire Team
5.11 | Submit Braid EMPE project | Benardette + Team

## RACI Chart
BRAID (EMPE) — RACI Matrix
R – Responsible: Does the work.
A – Accountable: Ultimately owns the outcome/decision.
C – Consulted: Provides expertise/input.
I – Informed: Needs to be kept updated.
Project Activity / Deliverable | Benardette – PM | Eulleria – Data | Jeff – Cybersecurity | Omogbolaga – IT Automation
Project initiation & planning | A/R | C | C | C
Define project scope & objectives | A/R | C | C | C
Stakeholder identification & analysis | A/R | C | C | C
Requirements gathering | A/R | R | C | R
User/persona definition | A/R | R | C | C
Matching criteria development | A | R | C | R
Matching algorithm / logic | C | A/R | C | R
Data structure & data management | C | A/R | C | R
Platform/technical development | C | C | C | A/R
Cybersecurity & privacy requirements | C | C | A/R | R
User access & authentication considerations | C | C | A/R | R
Risk identification & monitoring | A/R | C | R | R
Testing & quality assurance | A | R | R | R
User acceptance testing | A/R | R | C | R
Project documentation | A/R | C | C | C
Progress monitoring & reporting | A/R | C | C | C
Team coordination & meetings | A/R | C | C | C
Final platform review | A | R | R | R
Final presentation & submission | A/R | C | C | C
Project closure & lessons learned | A/R | C | C | C