## WBS
Work Breakdown Structure — Community Mental Health Signposting Portal
WBS Code | Task / Work Package | Owner | Start Day | End Day | Duration (days) | Deliverable
1 | Kickoff & Problem Grounding
1.1 | Project Initiation (kickoff meeting, charter, WBS, stakeholder register) | Nelson Mukhwana (PM) | 1 | 3 | 3 | Project Charter, WBS, Stakeholder Register
1.2 | User Research (interviews/surveys on resource discovery) | Elsa Michaud (UX) | 1 | 3 | 3 | Research notes, target user groups
1.3 | Mental Health & Burnout Data Collection | Vivian Enenta (Data) | 1 | 3 | 3 | Research Dataset (raw)
1.4 | Security Risk Identification & Threat Assessment | Esther Omotayo-Omomule (Cyber) | 1 | 3 | 3 | Threat Assessment
1.5 | Hosting Options Review & Requirements Scoping | Michelle Agyapong (IT) | 1 | 3 | 3 | System Requirements (draft)
2 | Design & Planning
2.1 | GitHub Repository & Dev Environment Setup | Nelson Mukhwana (PM) | 4 | 4 | 1 | GitHub repo structure
2.2 | Personas, Journey Maps & Wireframes | Elsa Michaud (UX) | 4 | 6 | 3 | User Personas, User Flow, Wireframes
2.3 | High-Fidelity Mockups & Design System (start) | Elsa Michaud (UX) | 7 | 7 | 1 | Design System (draft)
2.4 | Security Architecture & Authentication Design | Esther Omotayo-Omomule (Cyber) | 4 | 6 | 3 | Security Architecture
2.5 | KPI Framework & Dashboard Design | Vivian Enenta (Data) | 4 | 6 | 3 | KPI Framework, dashboard layout
2.6 | Deployment Plan Drafting | Michelle Agyapong (IT) | 4 | 7 | 4 | Deployment Plan (draft)
3 | Build & Integrate
3.1 | Interactive Prototype Build (Figma) | Elsa Michaud (UX) | 8 | 9 | 2 | Figma Prototype
3.2 | Hosting & Deployment Setup | Michelle Agyapong (IT) | 8 | 10 | 3 | Staging environment
3.3 | Security Review of Prototype | Esther Omotayo-Omomule (Cyber) | 9 | 11 | 3 | Security review notes, fixes list
3.4 | KPI Dashboard Build | Vivian Enenta (Data) | 8 | 11 | 4 | KPI Dashboard (working)
3.5 | Bug List Coordination & Usability Pass | Nelson Mukhwana (PM) | 10 | 11 | 2 | Bug/fix tracker
4 | Testing & Documentation
4.1 | Final Report Compilation | Nelson Mukhwana (PM) | 12 | 13 | 2 | Final Report
4.2 | Design System Finalisation | Elsa Michaud (UX) | 12 | 12 | 1 | Design System (final)
4.3 | Deployment & Maintenance Plan Finalisation | Michelle Agyapong (IT) | 12 | 13 | 2 | Deployment Plan, Maintenance Plan, Support Guide
4.4 | Risk Assessment & Security Docs Finalisation | Esther Omotayo-Omomule (Cyber) | 12 | 12 | 1 | Risk Assessment, Data Protection Plan
4.5 | Data Deliverables Packaging | Vivian Enenta (Data) | 12 | 12 | 1 | Final dataset, charts, KPI framework
4.6 | GitHub Repository Cleanup & Documentation | Nelson Mukhwana (PM) | 13 | 13 | 1 | Organised GitHub repo
5 | Final Submission
5.1 | Rehearse & Deliver Final Presentation | Whole Team | 14 | 14 | 1 | Final Presentation
5.2 | Submit All Deliverables | Nelson Mukhwana (PM) | 14 | 14 | 1 | Full deliverable set submitted
Owner Colour Key (used on the Gantt Chart tab):
Nelson Mukhwana (PM) | Elsa Michaud (UX) | Michelle Agyapong (IT) | Esther Omotayo-Omomule (Cyber) | Vivian Enenta (Data) | Whole Team

## Gantt Chart
Gantt Chart — Community Mental Health Signposting Portal (14-Day Sprint)
Start Date (Day 1): | 2026-07-20
WBS | Task / Work Package | Owner | Start | End | Dur. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| Date → |  |  |  |  | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02
1 | Kickoff & Problem Grounding |  | 1 | 3 | 3 | bar: 2026-07-20 to 2026-07-22
1.1 | Project Initiation (kickoff meeting, charter, WBS, stakeholder register) | Nelson Mukhwana (PM) | 1 | 3 | 3
1.2 | User Research (interviews/surveys on resource discovery) | Elsa Michaud (UX) | 1 | 3 | 3 | bar: 2026-07-20 to 2026-07-22
1.3 | Mental Health & Burnout Data Collection | Vivian Enenta (Data) | 1 | 3 | 3
1.4 | Security Risk Identification & Threat Assessment | Esther Omotayo-Omomule (Cyber) | 1 | 3 | 3 | bar: 2026-07-20 to 2026-07-22
1.5 | Hosting Options Review & Requirements Scoping | Michelle Agyapong (IT) | 1 | 3 | 3
2 | Design & Planning |  | 4 | 7 | 4 | bar: 2026-07-23 to 2026-07-26
2.1 | GitHub Repository & Dev Environment Setup | Nelson Mukhwana (PM) | 4 | 4 | 1
2.2 | Personas, Journey Maps & Wireframes | Elsa Michaud (UX) | 4 | 6 | 3 | bar: 2026-07-23 to 2026-07-25
2.3 | High-Fidelity Mockups & Design System (start) | Elsa Michaud (UX) | 7 | 7 | 1
2.4 | Security Architecture & Authentication Design | Esther Omotayo-Omomule (Cyber) | 4 | 6 | 3 | bar: 2026-07-23 to 2026-07-25
2.5 | KPI Framework & Dashboard Design | Vivian Enenta (Data) | 4 | 6 | 3
2.6 | Deployment Plan Drafting | Michelle Agyapong (IT) | 4 | 7 | 4 | bar: 2026-07-23 to 2026-07-26
3 | Build & Integrate |  | 8 | 11 | 4
3.1 | Interactive Prototype Build (Figma) | Elsa Michaud (UX) | 8 | 9 | 2 | bar: 2026-07-27 to 2026-07-28
3.2 | Hosting & Deployment Setup | Michelle Agyapong (IT) | 8 | 10 | 3
3.3 | Security Review of Prototype | Esther Omotayo-Omomule (Cyber) | 9 | 11 | 3 | bar: 2026-07-28 to 2026-07-30
3.4 | KPI Dashboard Build | Vivian Enenta (Data) | 8 | 11 | 4
3.5 | Bug List Coordination & Usability Pass | Nelson Mukhwana (PM) | 10 | 11 | 2 | bar: 2026-07-29 to 2026-07-30
4 | Testing & Documentation |  | 12 | 13 | 2
4.1 | Final Report Compilation | Nelson Mukhwana (PM) | 12 | 13 | 2 | bar: 2026-07-31 to 2026-08-01
4.2 | Design System Finalisation | Elsa Michaud (UX) | 12 | 12 | 1
4.3 | Deployment & Maintenance Plan Finalisation | Michelle Agyapong (IT) | 12 | 13 | 2 | bar: 2026-07-31 to 2026-08-01
4.4 | Risk Assessment & Security Docs Finalisation | Esther Omotayo-Omomule (Cyber) | 12 | 12 | 1
4.5 | Data Deliverables Packaging | Vivian Enenta (Data) | 12 | 12 | 1 | bar: 2026-07-31
4.6 | GitHub Repository Cleanup & Documentation | Nelson Mukhwana (PM) | 13 | 13 | 1
5 | Final Submission |  | 14 | 14 | 1 | bar: 2026-08-02
5.1 | Rehearse & Deliver Final Presentation | Whole Team | 14 | 14 | 1
5.2 | Submit All Deliverables | Nelson Mukhwana (PM) | 14 | 14 | 1 | bar: 2026-08-02
Owner Colour Key:
Nelson Mukhwana (PM) | Elsa Michaud (UX) | Michelle Agyapong (IT) | Esther Omotayo-Omomule (Cyber) | Vivian Enenta (Data) | Whole Team
Tip: change the Start Date in B2 and the Date row (row 5) recalculates automatically. Coloured bars mark which days (columns G:T) each work package is active on.