## Issues Log
Issue ID | Issue / Risk | Category | Impact on Project | Initial Status | Resolution / Mitigation | Current Status | Owner / Responsible Team | Follow-up / Next Action
ISS-001 | Communication issues at the beginning of the project | Communication / Team Coordination | Delayed responses, difficulty coordinating team activities, and potential delays in agreeing on project tasks and deliverables. | Open | Established a clearer communication structure, scheduled regular team meetings, used shared project communication channels, and clarified responsibilities and deliverables. | Resolved / Controlled | Project Manager / Entire Team | Maintain agreed communication channels and escalate unresolved communication gaps promptly.
ISS-002 | Erratic power supply | Infrastructure / Operations | Interrupted development, meetings, research, documentation and other project activities. | Open | Team members use available backup power options where possible, plan critical work around power availability, and continue work asynchronously when live collaboration is interrupted. | Ongoing / Mitigated | Entire Team | Continue backup-power planning and prioritize critical deliverables during available power windows.
ISS-003 | Poor / unstable internet signal | Infrastructure / Connectivity | Disrupted online meetings, collaboration, file sharing, research, development and access to project tools. | Open | Use alternative networks/hotspots where available, download essential resources for offline work, and use asynchronous communication when connectivity is poor. | Ongoing / Mitigated | Entire Team | Maintain alternative connectivity options and avoid making critical work dependent on one network.
ISS-004 | Scheduling and availability conflicts | Team Coordination | Not all team members may be available at the same time, affecting meetings, reviews and collaborative work. | Identified | Use scheduled recurring meetings, communicate availability in advance, and provide asynchronous tasks/materials for members who cannot attend. | Monitoring | Project Manager / Team Leads | Confirm attendance before major sessions and document decisions for absent members.
ISS-005 | Dependency on team members for specific deliverables | Project Execution | A delayed input from one contributor can hold up downstream activities. | Identified | Break deliverables into smaller tasks, assign clear owners, track dependencies, and communicate blockers early. | Monitoring | Project Manager / Workstream Owners | Review dependencies during sprint check-ins and reassign tasks where necessary.
ISS-006 | Coordination between design, product and development activities | Product / Technical | Potential mismatch between approved MVP design, requirements and implementation. | Identified | Use the approved Product Backlog, Sprint Backlog and MVP requirements as the shared reference point; conduct reviews before implementation of major features. | Controlled | Product / Design / Development | Keep requirements and implementation aligned through sprint reviews and backlog refinement.
ISS-007 | Limited time available for project execution | Schedule / Resource | Pressure to complete research, design, development, testing and documentation within the sprint timeframe. | Identified | Prioritize P0/MVP work, defer out-of-scope features, and use the Definition of Done to control completion quality. | Monitoring | Project Manager / Entire Team | Review sprint scope regularly and prevent scope creep.
ISS-008 | Potential scope creep during MVP development | Scope / Product | Additional features could consume sprint capacity and delay the approved MVP. | Identified | Use the approved Product Backlog and Sprint Backlog; keep integrations and advanced features outside the current sprint unless scope is formally changed. | Controlled | Project Manager / Product Owner | Record new requests in the backlog rather than adding them directly to the sprint.

## Status Summary
Status | Count
Resolved / Controlled | 1
Ongoing / Mitigated | 2
Monitoring | 3
Controlled | 1