## Risk Register
Risk ID | Category | Risk Description | Cause / Trigger | Potential Impact | Probability | Impact | Risk Rating | Mitigation / Preventive Action | Contingency / Response | Risk Owner | Status
R-001 | Communication | Poor communication between team members causes delays or duplicated work. | Unclear communication channels, delayed responses or incomplete handoffs. | Schedule delays, duplicated effort and missed deliverables. | Medium | High | High | Maintain regular meetings, shared documentation and clear communication channels. | Escalate unresolved blockers to the Project Lead and reassign tasks where necessary. | Project Lead | Mitigated
R-002 | Infrastructure | Erratic power supply interrupts development and meetings. | Unreliable electricity supply. | Interrupted development, meetings, research and documentation. | High | High | High | Use backup power where available and plan critical activities around power availability. | Continue affected work asynchronously and reschedule critical sessions. | Entire Team | Ongoing
R-003 | Infrastructure | Poor or unstable internet signal disrupts meetings, research, development and file sharing. | Unstable network connectivity. | Disrupted collaboration, online meetings, development and access to project tools. | High | High | High | Maintain alternative network/hotspot options and download essential resources. | Switch network/provider and continue offline work where possible. | Entire Team | Ongoing
R-004 | Schedule | Limited team availability delays planned activities. | Conflicting schedules or inability to attend project sessions. | Delayed decisions, reviews and deliverables. | Medium | Medium | Medium | Agree meeting schedules in advance and provide asynchronous tasks. | Reallocate tasks and adjust sprint sequencing. | Project Lead | Monitoring
R-005 | Scope | Scope creep introduces features outside the approved MVP. | Additional feature requests during development. | Reduced sprint capacity and delayed MVP delivery. | Medium | High | High | Use the approved Product Backlog and formal change control. | Move additional features to the Product Backlog for future sprints. | Product Owner | Controlled
R-006 | Dependency | Delay in one team's deliverable blocks dependent activities. | Upstream work is not completed on time. | Downstream tasks and sprint commitments are delayed. | Medium | High | High | Track dependencies through the WBS and sprint planning. | Reassign work or temporarily prioritize independent tasks. | Project Lead | Monitoring
R-007 | Requirements | Unclear or changing requirements result in rework. | Incomplete requirements or late changes. | Development rework, wasted capacity and schedule impact. | Medium | High | High | Maintain approved requirements, acceptance criteria and backlog refinement. | Clarify requirements before affected development continues. | Product Owner | Controlled
R-008 | Technical | Integration or implementation difficulties delay MVP development. | Unexpected technical complexity or integration challenges. | Feature delays and possible reduction of MVP scope. | Medium | High | High | Technical planning, incremental development and early testing. | Simplify implementation or defer non-critical functionality. | Technical Lead | Monitoring
R-009 | Security | Unauthorized access to contracts, invoices or user information. | Weak authentication, access control or security configuration. | Confidentiality breach, loss of trust and potential compliance consequences. | Low | Very High | High | Authentication, access control, secure storage, encryption and security testing. | Disable affected functionality, investigate and remediate the issue. | Technical Lead | Open / Monitoring
R-010 | Data | Loss or corruption of contracts, invoices or project records. | Storage failure, accidental deletion or data corruption. | Loss of important contractual and payment evidence. | Low | Very High | High | Secure storage, backups and controlled data handling. | Restore from backup and investigate affected records. | Technical Lead | Open / Monitoring
R-011 | Security | Malicious or unsafe uploaded files compromise the application. | Unvalidated or malicious file uploads. | Security incident, application compromise or data exposure. | Medium | High | High | File validation, restricted file types, secure storage and upload controls. | Quarantine/remove affected files and investigate. | Development / QA | Monitoring
R-012 | Product | MVP fails to adequately address freelancer needs. | Insufficient user validation or mismatch between requirements and user workflows. | Low user satisfaction and poor adoption. | Medium | High | High | User research, requirements validation and usability testing. | Prioritize feedback-driven improvements before wider rollout. | Product Owner | Monitoring
R-013 | Adoption | Freelancers do not consistently use the platform after registration. | Poor onboarding, unclear value proposition or usability barriers. | Low active-user rate and weak product traction. | Medium | High | High | Simple UX, onboarding, reminders and continuous user feedback. | Investigate adoption barriers and improve onboarding/product experience. | Product Owner | Monitoring
R-014 | Quality | Critical defects remain unresolved before MVP release. | Insufficient testing time or incomplete defect resolution. | Unreliable product and delayed release. | Medium | High | High | Defined acceptance criteria, QA testing and defect tracking. | Delay release until critical defects are resolved. | QA Lead | Monitoring
R-015 | Stakeholder | Stakeholder feedback arrives late or conflicts with approved requirements. | Late reviews, unclear decision ownership or competing expectations. | Rework, delays and stakeholder dissatisfaction. | Medium | Medium | Medium | Establish clear review points and decision ownership. | Product Owner makes the prioritization decision and records it. | Project Lead | Monitoring
R-016 | Schedule | Sprint work is carried over because planned capacity exceeds available capacity. | Overcommitment or inaccurate estimation. | Sprint goals missed and delivery timeline extended. | Medium | Medium | Medium | Prioritize P0/MVP work and estimate sprint capacity realistically. | Move unfinished work back to the Product Backlog and reprioritize. | Scrum Team | Monitoring
R-017 | Compliance | Product handling of contracts and personal information does not meet applicable privacy requirements. | Privacy/security requirements not addressed early enough. | Compliance exposure, redesign and possible release delay. | Low | Very High | High | Include privacy/security requirements during design and development. | Conduct a compliance review and remediate before release. | Technical / Product Lead | Open / Monitoring
R-018 | Performance | Application becomes slow or unreliable as users, contracts and invoices increase. | Insufficient performance planning or growing system load. | Poor user experience and reduced reliability. | Medium | High | High | Performance testing and monitoring before and after deployment. | Optimize infrastructure/application and prioritize performance fixes. | Technical Lead | Monitoring
R-019 | KPI / Measurement | Insufficient usage data makes it difficult to measure product success. | KPI events or measurement methods are not implemented consistently. | Unable to establish reliable product-performance baselines. | Medium | Medium | Medium | Define KPI events and measurement methods before the pilot. | Establish the baseline during the pilot and revise measurement approach. | Product / PM | Open / Monitoring
R-020 | External Dependency | External services or infrastructure become unavailable. | Third-party service outage or dependency failure. | Temporary loss of affected functionality or development disruption. | Medium | Medium | Medium | Avoid unnecessary single points of dependency and document alternatives. | Switch to an available alternative service or operate the affected function asynchronously. | Technical Lead | Monitoring

## Risk Rating Guide
Risk Score | Rating | Recommended Action
1–4 | Low | Monitor
5–9 | Medium | Mitigate and monitor
10–16 | High | Active mitigation required
17–25 | Critical | Immediate escalation and response
Scoring Method | Probability × Impact
Probability | Low / Medium / High
Impact | Low / Medium / High / Very High

## Risk Summary
Status | Number of Risks
Mitigated | 1
Ongoing | 2
Monitoring | 11
Controlled | 2
Open / Monitoring | 4