TEAM BEACON COLLABORATIVE

Implementation Plan Document

Surplus Food Redistribution Network  |  UN SDG 2: Zero Hunger  |  Grow with Google × Mentor Me Collective BUILD Project, 2026

Problem Statement: Local grocery vendors dump surplus perishable items due to a lack of an automated, hyper-local coordination hub for local pantries.

# 1. Objective

Deploy a pilot of the Surplus Food Redistribution Network in Chicago, starting in the highest-need, highest-opportunity community area identified by our research (West Garfield Park), then expanding to adjacent priority areas guided by our Food Access Gap Score.

# 2. Phased Rollout

Phase 1. Foundation (Weeks 1-4)

Goal: Complete the data foundation and secure the first pilot partners.

- Finalize the location dataset for all 10 originally identified priority areas (6 of 10 currently complete; East Garfield Park, Kenwood, Lake View, and Chatham remain)

- Confirm with Chicago Food Rescue and the Greater Chicago Food Depository that target vendors/pantries are not already in their active networks, so the pilot stays complementary rather than duplicative

- Recruit the first cohort of vendors and pantries in West Garfield Park

- Finalize the platform's role, verification, and security model

- Finalize the frontend screen designs and design system

Resources needed: team time; Google Places API access; outreach contact list for GCFD/Chicago Food Rescue

Phase 2. MVP Build (Weeks 5-8)

Goal: Build and internally test a working version of the platform.

- Build the core listing/matching application (Google Maps API + Firestore, or equivalent)

- Implement organization verification and role-based dashboards for Donor, Recipient, and Administrator

- Integrate SMS/WhatsApp fallback notifications for low-connectivity organizations

- Run a small internal pilot with 5 vendors and pantries

Resources needed: cloud hosting (free/education tier); SMS gateway credits (Twilio-equivalent); developer time

Phase 3. Pilot & Measure (Weeks 9-12)

Goal: Run a live pilot and use real data to guide expansion.

- Run the live pilot in West Garfield Park

- Track KPIs (grocery/pantry density, pantry-to-grocery ratio, Food Access Gap Score) via the live Tableau dashboard

- Expand into Austin and Auburn Gresham, the next-highest-priority areas by Food Access Gap Score

Resources needed: volunteer coordinators; ongoing dashboard maintenance

# 3. Resource Summary

| Resource | Phase | Purpose |
| --- | --- | --- |
| Google Places / Maps API | 1-3 | Location data & proximity matching |
| Cloud hosting (free/education tier) | 2-3 | Application backend |
| SMS gateway (Twilio-equivalent) | 2-3 | Low-connectivity fallback |
| Volunteer coordinators | 3 | Pilot outreach & support |
| Team time across all 5 tracks | 1-3 | Design, build, secure, test, coordinate |

# 4. Risk & Mitigation

| Risk | Likelihood/Impact | Mitigation |
| --- | --- | --- |
| Vendor reluctance due to liability fear | Medium / High | Cite Bill Emerson Act & Illinois Good Samaritan protections directly in onboarding materials |
| Overlap with Chicago Food Rescue / GCFD | Medium / Medium | Direct partnership conversation before launch; target only under-covered vendors/pantries |
| Incomplete location data (4 of 10 priority areas still uncollected) | Medium / Medium | Phased data collection for remaining areas before wider rollout |
| Low tech adoption among small vendors/pantries | Medium / Medium | SMS/WhatsApp fallback and a sub-1-minute listing flow; no app install required |
| Unauthorized access to organization or reservation data | Medium / High | Server-enforced, role-based access control and mandatory organization verification |
| Platform or service unavailability during time-senstivie pickups | Medium / Medium | Predictable failure handling, monitoring, and recoverable data storage |

# 5. Success Metrics

Tracked via the live Tableau dashboard :

- Grocery Density per 10k / Pantry Density per 10k

- Pantry-to-Grocery Ratio

- Food Access Gap Score (composite priority indicator)

- Vendor Recruitment Target Count

# 6.Team Ownership

| Track | Primary Responsibility in this plan |
| --- | --- |
| Project Managemetn | Overall coordination, timeline tracking, documentation cohesion. |
| Cybersecurity | Access control, vericationworkflow, data protection, security testing. |
| Data Analytics | Reserach, dataset, KPIs, dashboard, priority-area analysis. |
| IT Support | Environment setup, deployment support, run/view instruction. |
| IT Automation / Python | Core application build, matching logic, automation. |